## Sheet1
Iteration	Task	Assignee	Est. Hours	Actual Hours	Notes
1	Assign roles	All	1		We’ll probably just do this over slack
	Research front end frameworks	Aaron, Sang	2		Research options and present findings to team
	Research back end frameworks	Nathan, Nathaniel	2		Research options and present findings to team
	Pick frameworks for front and back end	All	1		We’ll do this over slack based on the recommendations of the researchers
	Baseline Requirements	Eric	2	5
	Write Project Plan	Sang	3
	Write Project Charter	Nathan	2

	Totals		13	5

2	Initial Code Commit		2		Must be done early in sprint. Create the web app and push the code to github.
	Technical prototype				Due in the sprint but seems extremely premature. Hopefully more info is forthcoming
	Add New Show	None (parent task)	20	0	Don’t Log time against this directly
	Create data model for Shows and data base		5		Should at least support reads and writes. For now only attribute is Name(non-nullable)
	Create views for Shows		5		One view to list all Shows, One view to add shows. Only attribute is Name
	Create Controller for Shows		5		Should support Get all and Post
	Integration testing/seed data		5		Make sure shows can be created and displayed via UI. Create several shows to seed the db.

	Totals		22	0