## Sheet1
Iteration	Task	Assignee	Est. Hours	Actual Hours	Notes
1	Assign roles	All	1	2.5	We’ll probably just do this over slack
	Research front end frameworks	Aaron, Sang	2	5	Research options and present findings to team
	Research back end frameworks	Nathan, Nathaniel	2	2	Research options and present findings to team
	Pick frameworks for front and back end	All	1	2.5	We’ll do this over slack based on the recommendations of the researchers
	Baseline Requirements	Eric	2	5
	Write Project Plan	Sang	3	8
	Write Project Charter	Nathan	2	4

	Totals		13	29

2	Initial Code Commit	Eric	2		Must be done early in sprint. Create the web app and push the code to github.
	Technical prototype	All	2		Due in the sprint but seems extremely premature. Hopefully more info is forthcoming. Estimated high to account for unknowns
	Create M, V and C for endpoints	None (parent task)	25	0	Don’t Log time against this directly
	MVC for External Users	Nathan	5		Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.
	MVC for Admin Users	Sang	5		Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.
	MVC for Shows	Arron	5		Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.
	MVC for Services	Nathaniel	5		Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.
	MVC for Recommendations	Eric	5		Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.

	Totals		34	0