## Sheet1
Iteration	Task	Assignee	Est. Hours	Actual Hours	Notes
1	Assign roles	All	1	2.5	We’ll probably just do this over slack
	Research front end frameworks	Aaron, Sang	2	5	Research options and present findings to team
	Research back end frameworks	Nathan, Nathaniel	2	2	Research options and present findings to team
	Pick frameworks for front and back end	All	1	2.5	We’ll do this over slack based on the recommendations of the researchers
	Baseline Requirements	Eric	2	5
	Write Project Plan	Sang	3	8
	Write Project Charter	Nathan	2	4

	Totals		13	29

2	Initial Code Commit	Eric	2	1	Must be done early in sprint. Create the web app and push the code to github.
	Technical prototype	All	2	2.5	Due in the sprint but seems extremely premature. Hopefully more info is forthcoming. Estimated high to account for unknowns
	Create M, V and C for endpoints	None (parent task)	25	22	Don’t Log time against this directly
	MVC for External Users	Nathan	5	8	Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.
	MVC for Admin Users	Sang	5	12	Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.
	MVC for Shows	Arron	5	1	Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.
	MVC for Services	Nathaniel	5	1	Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.
	MVC for Recommendations	Eric	5	5	Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.

	Totals		34	25.5

3	Research Login Functionality and assess resource needs	Nathan, Aaron	8		ASP.Net Core probably has a standard library/set of tools for secure login. (ASP.NET Core Identity seems to be the one.) We can surmise if this will be more than one person can handle and go from there.
	Create service provider search based on selected shows	Nathaniel	2		This will be able to save a list of shows and then check which streaming services have those shows.
	Create reccomendations page	Sang	5		This may actually feed recommendations on multiple pages, and/or we will combine certain pages if needed.
	MVC for admin helpdesk	Aaron	5		This would probably be a Entity Set (A Table in the DB) of messages, the user who sent the message, and other details.
	Clean up database situation	Eric	5		Make all the models use a single database context to the same database.

	Totals		25	0
Iteration	Task	Assignee	Est. Hours	Actual Hours	Notes
1	Assign roles	All	1	2.5	We’ll probably just do this over slack
	Research front end frameworks	Aaron, Sang	2	5	Research options and present findings to team
	Research back end frameworks	Nathan, Nathaniel	2	2	Research options and present findings to team
	Pick frameworks for front and back end	All	1	2.5	We’ll do this over slack based on the recommendations of the researchers
	Baseline Requirements	Eric	2	5
	Write Project Plan	Sang	3	8
	Write Project Charter	Nathan	2	4

	Totals		13	29

2	Initial Code Commit	Eric	2	1	Must be done early in sprint. Create the web app and push the code to github.
	Technical prototype	All	2	2.5	Due in the sprint but seems extremely premature. Hopefully more info is forthcoming. Estimated high to account for unknowns
	Create M, V and C for endpoints	None (parent task)	25	22	Don’t Log time against this directly
	MVC for External Users	Nathan	5	8	Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.
	MVC for Admin Users	Sang	5	12	Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.
	MVC for Shows	Arron	5	1	Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.
	MVC for Services	Nathaniel	5	1	Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.
	MVC for Recommendations	Eric	5	5	Add whatever atomic attributes you can think of in the model. Only support get all and put in the controller. Scaffold generated view is fine for now.

	Totals		34	25.5

3	Research Login Functionality and assess resource needs	Nathan, Aaron	8	12	ASP.Net Core probably has a standard library/set of tools for secure login. (ASP.NET Core Identity seems to be the one.) We can surmise if this will be more than one person can handle and go from there.
	Create service provider search based on selected shows	Nathaniel	2	2	This will be able to save a list of shows and then check which streaming services have those shows.
	Create reccomendations page	Sang	5	5	This may actually feed recommendations on multiple pages, and/or we will combine certain pages if needed.
	MVC for admin helpdesk	Aaron	5	2	This would probably be a Entity Set (A Table in the DB) of messages, the user who sent the message, and other details.
	Clean up database situation	Eric	5	7	Make all the models use a single database context to the same database.

	Totals		25	28

4	Lock down shows and services endpoints	Nathaniel	8
	Header links specific to user role	Aaron	8	6
	Set up identity roles, users, login	Nathan, Aaron	8	12
	Implement multi-show search and single show search	Eric	8
	Add some realistic seed data for shows and services	Sang	8	6
	Create Architecture Document	Eric	8	5
	Lock down user endpoints	Nathan
			48	29
	Totals