## Sheet1
Iteration	Task	Assignee	Est. Hours	Actual Hours	Notes
1	Assign roles	All	1		We’ll probably just do this over slack
	Research front end frameworks	Aaron, Sang	2		Research options and present findings to team
	Research back end frameworks	Nathan, Nathaniel	2		Research options and present findings to team
	Pick frameworks for front and back end	All	1		We’ll do this over slack based on the recommendations of the researchers
	Baseline Requirements	Eric	2
	Write Project Plan	Sang	3
	Write Project Charter	Nathan	2

	Totals		13	0